## Sheet1
Goal | MOS | Key Tasks | Limiting factors | Questions | Key players | Timeline/Date
Create Presentation | (Below) | Compile information (see below) | Have to read all reports and learn a lot of theory |  | Me, Carl? | 2018-03-01
Create Presentation | Finishing powerpiont | Create Powerpoint | Work getting it to be asthetically pleasing |  | Me | 2018-03-14
Create Presentation | Speech finished | Prepare Speech | Have to write a long speech and time it |  | Me, Carl? | 2018-03-20
Create Presentation | Speech is memorized | Practice Speech | Time to practice |  | Me, Carl, Friends | 2018-04-01
Create Presentation | Get thorugh presentation without sounding like a dingus | Present | Nerves |  | Me | 2018-04-01
Reduce last galaxy | Finish reducing | Start reduction | Need to receive it from Carl |  | Carl | 2018-03-14
Reduce last galaxy | Plot has all points | Put reduced info into plot | Recall how to do everything |  | Me | 2018-03-14
Reduce last galaxy | Plot looks good and Everyone who sees it loves it. | Make things look pretty | Make sure everything is in the right place |  | Me, Carl | 2018-03-14
Get ready for Denver | Finish maknig poster | Make poster | Craft supplies and putting together |  | Me, Carl | 2018-06-01
Get ready for Denver | Get speech memorized | Prepare speech for there | Write a speech that is a good length |  | Me | 2018-06-01
Get ready for Denver | Get Rooms and transportation booked | Get booking figured out | Don't know who should go about that |  | Me, Carl | 2018-06-01
Get ready for Denver | Arrive! | Go to Denver | Get on the Plane! |  | Me | 2018-06-01
Get ready for Denver | Survive the judgment | Present | Nerves |  | Me | 2018-06-01
Compile Information | Finish all papers | Read papers | Lots to read |  | Me | 2018-03-01
Compile Information | Write notes and get ready to transfer | Take Notes | Lots to take notes on |  | Me | 2018-03-01
Compile Information | Put all notes on OSF and ask good questions on them | Put all notes together on OSF | Just time |  | Me | 2018-03-01
Get the Tavel Money | Finish rough draft and then clean up from there | Write Abstract | Have to get my goals and theory all figured out |  | Me, Carl | 2018-04-01
Get the Tavel Money | Finish form | Fill out rest of form | Have to get my goals and theory all figured out |  | Me, Carl | 2018-04-01
Get the Tavel Money | Turn in | Turn in time | Have to get my goals and theory all figured out |  | Me, Carl | 2018-04-01
Beginning of strategic plan
Goal | Task | Components 1---# | end Date | Duration | Start date
Create Presentation | Compile information | Read papers | 2018-03-01 | 1 | 2018-02-28
| Compile information | Take Notes | 2018-03-01 | 1 | 2018-02-28
| Compile information | Put notes on OSF | 2018-03-01 | 1 | 2018-02-28
Create Presentation | Create Powerpoint | Create scafolding | 2018-03-01 | 5 | 2018-02-24
| Create Powerpoint | Fill in some information | 2018-03-01 | 3 | 2018-02-26
| Create Powerpoint | Insert Pictures and graphs | 2018-03-01 | 3 | 2018-02-26
| Create Powerpoint | Polish | 2018-03-10 | 4 | 2018-03-06
| Create Powerpoint | Form speech around | 2018-03-14 | 4 | 2018-03-10
Create Presentation | Prepare Speech | Create rough draft | 2018-03-14 | 2 | 2018-03-12
| Prepare Speech | Show to Carl | 2018-03-16 | 1 | 2018-03-15
| Prepare Speech | Revise | 2018-03-17 | 1 | 2018-03-16
| Prepare Speech | Show to Carl | 2018-03-18 | 1 | 2018-03-17
| Prepare Speech | Finshing touches | 2018-03-20 | 1 | 2018-03-19
Create Presentation | Practice Speech | Practice at home/Alone | 2018-03-21 | 2 | 2018-03-19
| Practice Speech | practice in front of someone | 2018-03-24 | 3 | 2018-03-21
| Practice Speech | Show to Carl | 2018-03-27 | 1 | 2018-03-26
| Practice Speech | Add anything necessary | 2018-03-31 | 2 | 2018-03-29
Create Presentation | Present | Show up early | 2018-04-01 | 1 | 2018-03-31
| Present | Run through a few times | 2018-04-01 | 1 | 2018-03-31
| Present | Present to group | 2018-04-01 | 1 | 2018-03-31
0
Reduce Last galaxy | Start reduction | Receive galaxy from Carl | 2018-03-10 | 1 | 2018-03-09
| Start reduction | Go through notes and computer | 2018-03-10 | 1 | 2018-03-09
| Start reduction | Make nice data (imFit, imStat, etc) | 2018-03-10 | 5 | 2018-03-05
| Start reduction | Make Ionized Oxygen stuff too | 2018-03-14 | 5 | 2018-03-09
Reduce Last galaxy | Put reduced data into plot | Finish reduction | 2018-03-14 | 5 | 2018-03-09
| Put reduced data into plot | Put reduced data thorugh calculator function | 2018-03-14 | 2 | 2018-03-12
| Put reduced data into plot | Put new data into the plot | 2018-03-14 | 2 | 2018-03-12
| Put reduced data into plot | Also plot Oxygen stuff | 2018-03-14 | 5 | 2018-03-09
Reduce Last galaxy | Make things look pretty | Play around with plots to make sure everything looks good. | 2018-03-14 | 2 | 2018-03-12
| Make things look pretty | Make sure colors are able to be seen clearly | 2018-03-14 | 1 | 2018-03-13
| Make things look pretty | Other finishing touches | 2018-03-14 | 1 | 2018-03-13
0
Get ready for Denver | Make poster | Look on OSF page for examples and such | 2018-06-01 | 20 | 2018-05-12
| Make poster | Transfer some stuff from current presentation | 2018-06-01 | 20 | 2018-05-12
| Make poster | Make things aestheticly pleasing | 2018-06-01 | 20 | 2018-05-12
| Make poster | Show to Carl, revise and repeat until finished | 2018-06-01 | 18 | 2018-05-14
Get ready for Denver | Prepare Speech | Take current speech from WSU seminar | 2018-06-01 | 17 | 2018-05-15
| Prepare Speech | Shorten the speech to 5 to 10 minutes | 2018-06-01 | 17 | 2018-05-15
| Prepare Speech | Corelate speech to new poster | 2018-06-01 | 16 | 2018-05-16
| Prepare Speech | Practice on friends, Carl, and by myself | 2018-06-01 | 14 | 2018-05-18
| Prepare Speech | Revise until appropriate length and jargon usage. | 2018-06-01 | 14 | 2018-05-18
Get ready for Denver | Get booking figured out | Get travel funds (which requires that I finish abstract) | 2018-03-01 | 1 | 2018-02-28
| Get booking figured out | Go to AAS website for details on the stay | 2018-03-01 | 1 | 2018-02-28
| Get booking figured out | Book room, and plane, for Carl and I | 2018-03-01 | 1 | 2018-02-28
| Get booking figured out | Keep booking information in safe and secure place | 2018-03-01 | 1 | 2018-02-28
Get ready for Denver | Go to Denver | Travel to Minneapolis airport | 2018-06-01 | 2 | 2018-05-30
| Go to Denver | Board plane to Denver | 2018-06-01 | 2 | 2018-05-30
| Go to Denver | Arrive at Denver | 2018-06-01 | 2 | 2018-05-30
| Go to Denver | Find ride to Hotel | 2018-06-01 | 2 | 2018-05-30
| Go to Denver | Set up camp for the day | 2018-06-01 | 2 | 2018-05-30
| Go to Denver | Prepare for day of presentation | 2018-06-01 | 2 | 2018-05-30
Get ready for Denver | Present | Wake up and get all nicely dressed | 2018-06-01 | 1 | 2018-05-31
| Present | Go to presentation area | 2018-06-01 | 1 | 2018-05-31
| Present | Wait for judges to come by, give speech to any passerbys | 2018-06-01 | 1 | 2018-05-31
| Present | Present to judges. | 2018-06-01 | 1 | 2018-05-31
0
Get travel money | Write abstract | Write rough draft | 2018-03-01 | 7 | 2018-02-22
| Write abstract | Revise under Carls supervision | 2018-03-01 | 7 | 2018-02-22
| Write abstract | Create final product to send for AAS and travel funds | 2018-03-01 | 7 | 2018-02-22
Get travel money | Fill out form | Meet with Carl | 2018-03-01 | 1 | 2018-02-28
| Fill out form | Fill out all of form | 2018-03-01 | 1 | 2018-02-28
Get travel money | Turn In | Turn in | 2018-03-01 | 1 | 2018-02-28
Formulas:
Key players = [Limiting factors]-[Questions]