## Sheet1
Goal | MOS | Key Tasks | Limiting factors | Questions | Key players | Timeline/Date
Create GUI | Completed GUI: Easy to use, looks clean, works well | Learn how the GUI works | Time for research |  | Me | 2019-08-14
Create GUI | Completed GUI: Easy to use, looks clean, works well | Research possible GUI, pick best one | Must be compatible with rest of design |  | Me, Carl | 2019-08-14
Create GUI | Completed GUI: Easy to use, looks clean, works well | Research possible GUI, pick best one | Unsure what inputs will be relevant |  | Me | 2019-08-14
Create GUI | Completed GUI: Easy to use, looks clean, works well | Implement GUI | Knowledge of Python |  | Me | 2019-08-14
Create GUI | Completed GUI: Easy to use, looks clean, works well | Create inputs for variables | Knowledge of Astrophysics |  | Me, Carl | 2019-08-14
Create GUI | Completed GUI: Easy to use, looks clean, works well | Output input variables to appropriate Python code | Knowledge of Python |  | Me | 2019-08-14
Create GUI | Remotely accessible | Familiarize myself with remote connections | GUI must be remotely accessible |  | Me, Carl, Adam? | 2019-08-14
Raspberry Pi gives Arduino outputs | Implement a communication protocol between Pi and Arduino | Research protocols | Research time, Carl's opinion |  | Me | 2019-06-01
Raspberry Pi gives Arduino outputs | Implement a communication protocol between Pi and Arduino | Determine which protocol to use | Research time, Carl's opinion | What do I use? I2C? | Me, Carl | 2019-06-01
Raspberry Pi gives Arduino outputs | Implement a communication protocol between Pi and Arduino | Establish initial communication between Pi and Arduino | Knowledge of Python and I2C |  | Me | 2019-06-10
Raspberry Pi gives Arduino outputs | Implement a communication protocol between Pi and Arduino | Build a feedback routine between Pi and Arduino | Knowledge of Control Systems | What is the communication rate? | Me | 2019-06-20
Raspberry Pi takes ecliptic inputs and computes them | Computed ecliptics | Research the mathematics | Time for research | What are the relevant perameters of ecliptic tracking? | Me, Carl | 2019-06-20
Raspberry Pi takes ecliptic inputs and computes them | Computed ecliptics | Identify relevant variables | Time for research |  | Me, Carl | 2019-06-20
Raspberry Pi takes ecliptic inputs and computes them | Computed ecliptics | Implement mathematics | Knowledge of Python |  | Me, Carl, Adam? | 2019-06-30
Raspberry Pi takes ecliptic inputs and computes them | Computed ecliptics | Prep outputs for communication protocol | Knowledge of Python |  | Me | 2019-06-30
Raspberry Pi takes ecliptic inputs and computes them | Completed GUI: Easy to use, looks clean, works well | Implement GUI | Knowledge of Python |  | Me | 2019-07-01
Raspberry Pi takes ecliptic inputs and computes them | Completed GUI: Easy to use, looks clean, works well | Create inputs for variables | Knowledge of Astrophysics |  | Me, Carl | 2019-07-01
Raspberry Pi takes ecliptic inputs and computes them | Completed GUI: Easy to use, looks clean, works well | Output input variables to appropriate Python code | Knowledge of Python |  | Me | 2019-07-01
Complete Arduino package | Arduino communicates to SSR motor switches | Research motor control methods | Time for Research |  | Me | 2019-06-01
Complete Arduino package | Arduino communicates to SSR motor switches | Determine final wiring model for SSRs | Review necessary functionality | What's your function? | Me, Carl | 2019-06-20
Complete Arduino package | Arduino communicates to SSR motor switches | Mount motor switches to fixed piece of metal/wood | Finalized wiring diagram |  | Me | 2019-06-20
Complete Arduino package | Arduino communicates to SSR motor switches | Mount motor switches to fixed piece of metal/wood | Materials: wood/metal, ICB/IPCB | Wood or metal? | Me, Carl | 2019-06-20
Complete Arduino package | Arduino reads sensors | Determine final wiring model for sensors | Review necessary functionality | What's your function? | Me, Carl | 2019-06-30
Complete Arduino package | Arduino reads sensors | Solder sensor wiring to ICB | Finalized wiring diagram |  | Me | 2019-06-30
Complete Arduino package | Arduino reads sensors | Solder sensor wiring to ICB | Soldering time | ICB or IPBC? | Me | 2019-06-30